## Team Info and definitions
[5 empty] | Tracker Categories | Tracker Definitions
The Ferryman |  |  | Known Bugs | 33 | Issue Number | This is an increamented number for every bug found for a game. EX: If you must find 50 bugs for a group, your first bug entry is 1¦50.
|  |  | Open | 1 | Date found | The date that the bug was found
Team Members | Phone # | Email | In Progress | 0 | Build found | The current version of the build that is tested.
Kyle Bennett | 386 237 2692 | TelorathSennith@gmail.com | Duplicate - Waiting Confirmation | 1 | First
Marc Bordoy | 579 764 5570 | marcbordoy135@gmail.com | Not A Bug - Waiting Confirmation | 1 | Second
Drew Butikofer | 352 227 0124 | dbbutikofer@gmail.com | Known Shippable - Waiting Confirmation | 4 | Third
Test Student 4 |  |  | Fixed - Waiting Confirmation | 25 | Category | Indicate to the dev team what part of the game they will find the bug.
Test Student 5 |  |  | Can Not Reproduce - Waiting Confirmation | 1 | Art
Test Student 6 |  |  | Duplicate - Confirmed | 0 | Design
Test Student 7 |  |  | Not A Bug - Confirmed | 0 | Engineering
Test Student 8 |  |  | Known Shippable - Confirmed | 0 | Component | Additional detail for the dev team on where the bug can be found in the game.
Test Student 9 |  |  | Fixed - Confirmed | 0 | AI
Test Student 10 |  |  |  |  | Character
|  |  | Found Bugs | 52 | Combat
Game Dev Team Name |  |  | Open | 0 | Environment
Green Potatoes |  |  | In Progress | 0 | Fonts
|  |  | Duplicate - Waiting Confirmation | 2 | Gameplay
Team Members | Phone # | Email | Not A Bug - Waiting Confirmation | 8 | Input
Tarrent Adams | 806 292 6573 | adams.tarrent@gmail.com | Known Shippable - Waiting Confirmation | 5 | Logic
Yaniel Rivera | 787 342 9112 | yaniboy93@gmail.com | Fixed - Waiting Confirmation | 14 | Meshes
Young Kim | 407 534 7468 | youngkim8701@gmail.com | Can Not Reproduce - Waiting Confirmation | 5 | Networking
Tony Perez | 956 533 5872 | tonyboyangie3@gmail.com | Duplicate - Confirmed | 0 | Physics
Nathan Ralph | 513 280 0615 | naralph@outlook.com | Not A Bug - Confirmed | 1 | Sounds
Dev Student 6 |  |  | Known Shippable - Confirmed | 0 | Stats
Dev Student 7 |  |  | Fixed - Confirmed | 17 | Textures
Dev Student 8 |  |  |  |  | UI
Dev Student 9 |  |  |  |  | Severity | Severity indicates to the dev team what order the bug is addressed in. Crash bugs are addressed first, as they keep players from playing at all. Critical bug are next, and as they usually block gameplay. Minor bugs do not block gameplay, but are unsightly logic or artist problems.
Dev Student 10 |  |  |  |  | A - Crash/Showstoper
B - Critical
Number of bugs tester team must find |  |  |  |  | C - Minor
60 |  |  |  |  | D - Suggestion
[5 empty] | Summary | A one sentence description of the bug. EX: AI bugs found in level one would be "LVL1-AI".
First testing round due date |  |  |  |  | What was seen | A detailed description of what the tester was doing when the bug occurred. This will be immensely helpful to dev teams when the bug is hard to reproduce. The team can use this knowledge to draw correlations between this and other bugs.
### |  |  |  |  | What was expected | The Dev team will be better able to understand the bug when the tester adds information on what they expected to have happened
[5 empty] | Steps to reproduce | Detailed step by step instructions on how to reproduce the bug, if it is reproducible.
Second testing round due date |  |  |  |  | Reproduction Rate | The number of times the bug was reproduced. EX 2 of 5 tries
### |  |  |  |  | Status | This is a critical indicator to the dev team, and the production staff as to the status of a bugs. Until the bug is confirmed to be fixed, the bug must taken care of.
[5 empty] | Open | Bug entered but not adressed in any way
[5 empty] | In Progress | somone on the team is currently attempting to fix the issue
[5 empty] | Duplicate - Waiting Confirmation | Bug was previously submitted
[5 empty] | Not A Bug - Waiting Confirmation | The bug will not be fixed and is waiting to be closed
[5 empty] | Known Shippable - Waiting Confirmation | The team all agrees that this is an issue but is an issue that can not be adressed.
[5 empty] | Fixed - Waiting Confirmation | Dev teams believe the bug is fixed
[5 empty] | Can Not Reproduce - Waiting Confirmation | Dev team is unable to reproduce the bug on their computer
[5 empty] | Duplicate - Confirmed | Bug was previously submitted. Only APs can set this status
[5 empty] | Not A Bug - Confirmed | The issue listed was determined to be working as intended. Only APs can set this status
[5 empty] | Known Shippable - Confirmed | The team all agrees that this is an issue but is an issue that can not be adressed. Only APs can set this status
[5 empty] | Fixed - Confirmed | Fixed and the QA team has confimed that it is fixed. Only QA teammembers can set this status

## Found Bugs (Test Team)
Issue # | Status | Severity | Category | Component | Found By | Fixed By | Date found | Build found | Summary | Steps to reproduce | What was seen | What was expected | Progress Notes
1 | Fixed - Confirmed | C - Minor | Engineering | UI | Drew Butikofer | Tarrent Adams | 2016-05-18 | First | If Player moves in the tutorial, text overlaps and becomes unreadable | Go to Tutorial, move around | Tutorial UI overlapping | Tutorial UI not overlapping | This was a transparancy and placement issue, fixed by relayering all overlay objects, and editing some transparancies
2 | Fixed - Confirmed | B - Critical | Engineering | Input | Kyle Bennett | Tony Perez | 2016-05-18 | First | When entering hero mode and playing the game in a window, the mouse is not constrained within the window. Makes playing in window/hero mode unnecessarily difficult, especially if there is something behind the game window to click on which would lead to losing control of the game entirely until you tab back to it. | Play the game in windowed mode and enter hero mode. Attempt to turn rapidly. | Mouse can leave window easily | Mouse constrained to window
3 | Fixed - Confirmed | C - Minor | Engineering | UI | Drew Butikofer | Tarrent Adams | 2016-05-18 | First | Tutorial Box had no option to close out, until I walked over another tutorial "Area" | Could not find the exact way to reproduce | Tutorial overlay UI going blank no way to close out | The ability to close out | Thre was a single tutorial bix that was not connected to an overlay, it is a rare find, and took me multiple tries to reproduce. Should be fixed.
4 | Fixed - Confirmed | B - Critical | Engineering | Gameplay | Drew Butikofer | Tony Perez | 2016-05-18 | First | After playing tutorial, character selection gets turned off and your stuck playing Raven | Complete Tutorial go to play | Could not select player after tutorial was completed | Ability to select different characters
5 | Fixed - Confirmed | D - Suggestion | Engineering | UI | Kyle Bennett | Yaniel Rivera | 2016-05-18 | First | In hero mode, the mouse cursor is still visible. | Enter hero mode | Mouse still visible in hero mode | Mouse not visible in hero mode
6 | Fixed - Confirmed | C - Minor | Engineering | Gameplay | Drew Butikofer | Yaniel Rivera | 2016-05-18 | First | Theres no indication that other than movement that my minions are going to where i want them to in the tutorial, Sometimes they move other times they dont | Select minions and command them | Minions heading in a direction then stopping then heading to the bottom of the screen | Minions going to where i expected them to go | Added a straight line poiting to where the minion was commanded to walk towards; that is if the destination was set.
7 | Fixed - Confirmed | C - Minor | Design | UI | Marc Bordoy | Nathan Ralph | 2016-05-18 | First | WIthin the main menu the currently selected item color is alomst exaclty the sames ass the unselcted options |  | 5 blue buttons | the current key that is selected to turn into a color that in not blue | Made the buttons much darker when highlighted.
8 | Fixed - Confirmed | C - Minor | Engineering | UI | Drew Butikofer | Tarrent Adams | 2016-05-18 | First | Minimap doesnt make sense in tutorial, cant make out what is happening or what im selecting. |  | I can make out my hombase but all other UI I can't tell what it's representing | Mini map has clear representation of whats presented | Make the minimap show the entire tutorial as intended
9 | Fixed - Confirmed | C - Minor | Engineering | Gameplay | Drew Butikofer | Nathan Ralph | 2016-05-18 | First | In tutorial towers have little indication they're firing |  | Small projectiles then a -30 were all i had to know i was in range of being hit | Sounds, and a clear animation that im being fired upon. Tower is also kind of out of sight because of the height of the tower so animation is hard to see. | Included a ring that shows when a player is in range of the tower. Range updates depending on what type of shot is active.
10 | Not A Bug - Confirmed | D - Suggestion | Design | Input | Marc Bordoy | Tony Perez | 2016-05-18 | First | WASD Controls for menus and over head map movement. |  |  | movement with both WASD and arrow keys
11 | Fixed - Confirmed | C - Minor | Design | Gameplay | Drew Butikofer | Tarrent Adams | 2016-05-18 | First | Player can run outside but minimap only reflects the inside of the level |  | An outside level with seemingly no purpose | A clear learning experience leaving me with the no confusion about basic controls and objectives | This was a nav mesh obstical and bakeing issue. fixed by finding all objects without the correct coponent
12 | Fixed - Confirmed | B - Critical | Design | Gameplay | Kyle Bennett | Yaniel Rivera | 2016-05-18 | First | Hero has immense power that is almost unnecessary given the power of minions | Play game, enter hero mode. Push alongside minions, casually using abilities when there are enemies nearby to hit with them. | Since enemies have no hero, your power in any given lane is roughly twice theirs even when playing suboptimally. | Enemy team responds to the presence of player character in the lane more actively. The enemy must have a way to defend against the player's hero. | Upgraded AI. AI will scale in combat effectiveness with time along with other factors. AI will have a better late game but won't be easily killed in the early game as before
13 | Duplicate - Waiting Confirmation | B - Critical | Design | Environment | Drew Butikofer | Tarrent Adams | 2016-05-18 | First | Player can go through walls at multiple points in the Tutorial Level | Walls near portals and certain points along the level allow the player to escape outside | Player moved through walls | Player should not move through walls | This is a duplicate that was fixed with issue #11
14 | Fixed - Waiting Confirmation | C - Minor | Engineering | Input | Marc Bordoy | Tony Perez | 2016-05-18 | First | Quickly piviting will cuase the player to walk backward when holding fowards for about 1 second | walk fowards then move the mouse behind the hero | hero moon walking | a quick pivit in the other direction
15 | Can Not Reproduce - Waiting Confirmation | C - Minor | Design | Environment | Drew Butikofer | Tarrent Adams | 2016-05-18 | First | Objects in Tutorial that seem like they should be solid are not and the player can pass through them |  | Moving through objects | Player should not move through objects that look solid | This was an issue with nave mesh obsticals and baking, I had to find the specific obects, but should now be completely fixed (Update) This was reopened, and I searched the tutorial, as far as I can tell nothing is pass through able any more. Without knowing what to look at I just can not reproduce or find the object.
16 | Fixed - Confirmed | C - Minor | Engineering | Combat | Drew Butikofer | Nathan Ralph | 2016-05-18 | First | They're are no good indicators for the range of my attack or the range i can be attacked in |  | Nothing to indicate that I could attack or I could be attacked | Indication showing I can be attacked | Added a range indicator to towers while fixing another bug.
17 | Not A Bug - Waiting Confirmation | C - Minor | Engineering | Combat | Marc Bordoy | Tony Perez | 2016-05-18 | First | Able to use multiple abiltiys at the same time | press 1,2,3,4 simitaniusly | attacks happening at the same time | there being a wait time between using a firt and second spell | Following the example of other MOBAs, being able to use multiple spells simultaniously is valid. Granted, it is common to see one skill out of 4-5 with a cast time delay, however that usually is linked to balance.
19 | Fixed - Confirmed | B - Critical | Engineering | Input | Marc Bordoy | Tony Perez | 2016-05-18 | First | After dieing the map movent compleatly haulted | in the lower right area when i was in first person view i died to a tower kicked into the over head view and then i couldnt move. | the screne stuck on a perticual section of the map | being able to move the screen in over head view
20 | Known Shippable - Waiting Confirmation | C - Minor | Engineering | UI | Kyle Bennett | Tony Perez | 2016-05-18 | First | When clicking and dragging on the minimap to pan the camera, it creates a unit selection box | Click and drag on the minimap to pan the camera and create a unit selection box | Minimap has click and drag functionality for unit selection | Minimap does not have unit selection functionality or you cannot click and drag to pan the camera
22 | Fixed - Confirmed | C - Minor | Design | Character | Marc Bordoy | Tony Perez | 2016-05-18 | First | Character respawns in backwards. | When you respawn you have your back to the enemy | the hero watching the base | the hero to spawn in looking the way of the enemy
23 | Fixed - Confirmed | C - Minor | Design | Character | Marc Bordoy | Tony Perez | 2016-05-18 | First | No feedback when hero character get hit | Get hit | a bullet hiting the hero in the face | an ouch sound effect and red flashing
24 | Duplicate - Waiting Confirmation | C - Minor | Engineering | Character | Marc Bordoy | Yaniel Rivera | 2016-05-18 | First | Enemy AI does nothing to win | I stood still and didnt touch the game for 15 minuites and got a draw | no progrestion happining | I was expecting to lose | Similar to another bug report. Upgraded AI.
25 | Fixed - Waiting Confirmation | C - Minor | Engineering | Combat | Marc Bordoy | Nathan Ralph | 2016-05-18 | First | Cant tell the melee enemy are attacking | stand infront of enemys | Nothing i just got hit | some animation or signifier | Added particle effects on the ends of the swords that activate when melee minions attack.
26 | Fixed - Waiting Confirmation | C - Minor | Engineering | AI | Kyle Bennett | Tony Perez | 2016-05-18 | First | Minion pathing on top and bottom lane causes them to walk past rear tower while being fired upon | Bring your hero to top or bottom lane to kill the front turret, then escort your minions towards the rear turret. | Minions will go so far wide of turret many of them will not acquire it as a target to attempt to destroy it causing them to just be gunned down and accomplish nothing. | Minion pathing takes them straight through turret, allowing their AI to engage it and attempt to destroy it before moving onward.
27 | Not A Bug - Waiting Confirmation | B - Critical | Engineering | Character | Marc Bordoy | Tony Perez | 2016-05-18 | First | Not able to control the hero while in over head view | Go to over head view and pressing the usual movement buttons | the hero just standing and not following minion on clicking | I'm able to use hero ablitiys but have no other control over it
28 | Fixed - Confirmed | C - Minor | Engineering | UI | Kyle Bennett | Yaniel Rivera | 2016-05-18 | First | While in hero mode, RTS controls are still enabled. | Enter hero mode and use left/right click to select command your minions. | Minions can be controlled by your normal mouse controls while in hero mode though doing so is nearly impossible due to fighting with the mouse and camera being linked in a non 1:1 ratio | RTS controls are turned off while in hero mode or are linked to a cursor at the center of the screen to avoid me accidentally giving unwanted commands to my minions.
29 | Fixed - Confirmed | C - Minor | Engineering | UI | Kyle Bennett | Yaniel Rivera | 2016-05-18 | First | While in Hero Mode, changing camera angles with V does not remove you from hero mode, allowing you to continue controlling your character in an awkward manner, as well as causing an awkward billboarding problem with health bars | Enter Hero Mode and press the V key. Move the mouse and attempt to use Hero Mode Controls. | Player character's controls are still over-the-shoulder style from the birds-eye view. | Player's controls return to RTS if they change their camera angle. | Disabled movement but allowed to transition from the previous mode instead of forcing RTS.
30 | Fixed - Waiting Confirmation | B - Critical | Engineering | Gameplay | Drew Butikofer | Tarrent Adams | 2016-05-23 | Second | While in the tutorial, when you back up into your base the player gets stuck | Back up into your base | Player Stuck | Not getting stuck
31 | Fixed - Waiting Confirmation | B - Critical | Engineering | Character | Kyle Bennett | Young Kim | 2016-05-23 | Second | Princess's Hero abilities seem to have a duration of one frame | Pick Princess, begin the game. Enter hero mode. Use any of your abilities and watch them wear off nearly instantly. | Abilities wearing off instantly. | Abilities lasting several seconds. | Made all skills to last 3 seconds
32 | Fixed - Waiting Confirmation | D - Suggestion | Engineering | Gameplay | Drew Butikofer | Tony Perez | 2016-05-23 | Second | Abilities can be confusing by being able to select the ability and aim but not giving the user any indication that they dont have enough mana to actually do the attack. Please consider either not being able to select the ability at all when you dont have the mana or on keydown if not enough mana let me know through sound or visual indication that i must wait for mana to use my ability. |  |  |  | Hunter E ability no longer shows a range indicator when it isn't able to be fired.
33 | Not A Bug - Waiting Confirmation | C - Minor | Engineering | Combat | Marc Bordoy | Tarrent Adams | 2016-05-23 | Second | The character Raven Q/1 wasnt activating when i press those buttons | start a game with ravin | The abilities activated with a left click | THe ability actives when Q/1 is pressed | This is done on perpous, he ability is a skill shot, as such it shows an arrow to where it will go, and you click to use the skill.
34 | Fixed - Waiting Confirmation | C - Minor | Engineering | UI | Marc Bordoy | Young Kim | 2016-05-23 | Second | s/Tab opens shop but doesnt close it
35 | Known Shippable - Waiting Confirmation | C - Minor | Design | UI | Drew Butikofer |  | 2016-05-23 | Second | Pause menu and start menu have different controls as in one can be clicked and navigated by keyboard whereas the pause menu is only mouse |  | Differing controls | Either have all menus one control system or all of them both
36 | Fixed - Waiting Confirmation | A - Crash/Showstoper | Engineering | Character | Kyle Bennett | Yaniel Rivera | 2016-05-23 | Second | Game crashes if you use Caster's first ability in Hero mode the game crashes | Select the caster, press C to enter hero mode. Press 1 and click on an enemy. Game should Crash NOTE: Simply re-Targetting will put the bug in effect and crash unity, activating the skill doens't contribute to anything. | Game crashes. | Enemy minion is smote with magical fire. | Idk if the test team will read this but here is the thing. The wy I was diong targetting is based on rendering particles from th eminions sknned mesh renderer. Turns out there is a confirmed bug with assigning skinnedMeshRenderer to the particle system on script that crashes Unity. So the targetting has to be redone... yay...
37 | Fixed - Waiting Confirmation | C - Minor | Design | Environment | Drew Butikofer | Tarrent Adams | 2016-05-23 | Second | Mini-map mode in tutorial lets you see an unaccessible enemy base | Go to mini-map mode | The enemy base in mini map mode | I kept trying to access and send minions to enemy base without knowing its not a part of the tutorial | This was a main camera bounds issue, it was still allowing you to see area which was removed from the tutorial.
38 | Can Not Reproduce - Waiting Confirmation | C - Minor | Design | Gameplay | Drew Butikofer | Tarrent Adams | 2016-05-23 | Second | Enemies spawning outside the map shooting through walls | Could not reproduce | Enemies were spawning outside of the map | Enemies spawning in the arena
39 | Not A Bug - Waiting Confirmation | C - Minor | Engineering | Combat | Drew Butikofer | Tarrent Adams | 2016-05-23 | Second | Enemy towers health bar does not show up if your attacking it at a short range in the tutorial |  | When close to the enemy tower i could not see how much health the tower had | Seeing my targets health | The tower health never shows up in close range, no matter if you are in tutorial or main game. This is becasue the healthbar is above the tower, in order to see it the user has the ability to pan their camera using middle mouse button. The ability to look up and down is taught in the tutorial
40 | Not A Bug - Waiting Confirmation | C - Minor | Design | UI | Marc Bordoy | Tarrent Adams | 2016-05-23 | Second | When you start the tutorial it says press enter to skip | start tutorial | that screen came up | something that i can skip or the screen saying contiue instead of skip | This is becasue the intro screen that is shown was supposed to be a video, it is currently not useable becasue it causes a crash in everyone but the person who uploads the video. It was removed, with the plan to implement. The continue buttons in the tutorial are there to continue the tutorial, they are two differen comands and instructions
41 | Fixed - Waiting Confirmation | C - Minor | Engineering | UI | Drew Butikofer | Tony Perez | 2016-05-23 | Second | In the tutorial a notification lets you know that you will respawn but there is no timer to let you know how long that will be |  |  | A respawn indicator to let me know when I respawn
42 | Not A Bug - Waiting Confirmation | C - Minor | Engineering | Sounds | Marc Bordoy | Young Kim | 2016-05-23 | Second | Main menu audio does not start at 50% if you adjust aduio then close game and then open |  |  |  | Audio setting is to be saved and loaded back
43 | Known Shippable - Waiting Confirmation | D - Suggestion | Design | Environment | Drew Butikofer | Tarrent Adams | 2016-05-23 | Second | Tutorial does not contain any information on how to use the game store nor is it included anywhere but the key instruction screen |  |  | Tutorial to teach me all basic mechanics | This was removed due to time restraints. The tutorial was built by one person, and there was only so much that could be done. There is not enough time to script an entire nother section.
44 | Fixed - Waiting Confirmation | C - Minor | Engineering | UI | Kyle Bennett | Yaniel Rivera | 2016-05-23 | Second | Right Clicking in Hero control mode still creates the feedback that a command has been given. | Switch to hero mode and right click. | UI feedback that an order has been received | no feedback, because minions ignore the order. | Just Remover it entirely, it's usefullness had expired.
45 | Not A Bug - Waiting Confirmation | C - Minor | Engineering | Character | Marc Bordoy | Young Kim | 2016-05-23 | Second | defualt sencitivity with mouse movement way to fast |  | a slight movement with the mouse can send you spining
46 | Can Not Reproduce - Waiting Confirmation | B - Critical | Engineering | Input | Marc Bordoy | Tarrent Adams | 2016-05-23 | Second | Minions get stuck on walls and wont respawned to commands |  |  |  | I tried both of these multiple times with a good 60+ minions, I could not reproduce it. I do not thing this was just not a bug, but that it was fixed by a previous fix. Navmesh now blocks distance from walls, and sense they now stay in navigation mesh they respond to all comands.
47 | Can Not Reproduce - Waiting Confirmation | B - Critical | Engineering | Character | Marc Bordoy | Tarrent Adams | 2016-05-23 | Second | if to many minion gather around a wall they will force others in to the wall |  |  |  | I tried both of these multiple times with a good 60+ minions, I could not reproduce it. I do not thing this was just not a bug, but that it was fixed by a previous fix. Navmesh now blocks distance from walls, and sense they now stay in navigation mesh they respond to all comands.
48 | Fixed - Waiting Confirmation | C - Minor | Engineering | UI | Drew Butikofer | Tarrent Adams | 2016-05-23 | Second | Continue button in tutorial sometimes not working | not sure how to reproduce i think it has to do with moving around and clicking it after fighting minions |  |  | It was an error with toggleing the first information script. Should be fixed.
49 | Known Shippable - Waiting Confirmation | D - Suggestion | Engineering | Combat | Drew Butikofer |  | 2016-05-23 | Second | Range of abilities is hard to determine |  | Arrow is indicating direction but im not positive how far the attack goes | Range of my attacks | Hunter E range arrow shows actual range. The assassing has an arrow, which is the exact range of ability. This is kinda hard to determin but it was the best art asset we had access to.
50 | Fixed - Waiting Confirmation | D - Suggestion | Design | Gameplay | Kyle Bennett | Yaniel Rivera | 2016-05-23 | Second | Enemy core range is frustratingly large, able to kill melee characters before they can reach bottom/top tower. | Get anywhere near the enemy core and die horribly. |  | Enemy core kills the player if they get close enough to attack it
51 | Known Shippable - Waiting Confirmation | C - Minor | Engineering | Character | Marc Bordoy |  | 2016-05-23 | Second | if you gather to many minions some wioll stop responding to you | just keep your minions close to home basetill you have about 70 | many minions stuck on my base
52 | Fixed - Waiting Confirmation | C - Minor | Design | UI | Marc Bordoy | Young Kim | 2016-05-23 | Second | WIth in the character select screen the orange arrows are dulled out as if they were not selectable
53 | Not A Bug - Waiting Confirmation | C - Minor | Engineering | Combat | Marc Bordoy |  | 2016-05-23 | Second | I cant tell if the abilitys do anything
54 | Can Not Reproduce - Waiting Confirmation | C - Minor | Engineering | Combat | Kyle Bennett |  | 2016-05-23 | Second | Right clicking on an enemy minion while you have minions selected |  |  |  | Not sure what the bug summary means.
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Known Bugs (Dev Team)
Issue # | Status | Severity | Category | Component | Found By | Fixed By | Date found | Build found | Summary | Steps to reproduce | What was seen | What was expected | Progress Notes
2 | Can Not Reproduce - Waiting Confirmation | C - Minor | Engineering | Combat | Nathan Ralph | Tony Perez | 2016-05-18 | First | Projectiles from the towers persist after minions die occasionally. | 1. Get minions to a tower. 2. Have a minion die before the next projectile reaches it. | The projectile sticks around for a few seconds. | The projectile dissapears when reaching destination. | Despawn timer added to prevent projectiles hanging around forever.
3 | Fixed - Waiting Confirmation | C - Minor | Engineering | Character | Nathan Ralph | Nathan Ralph | 2016-05-18 | First | Special effect shows at the beginning of the game for the Hunter. | 1. Start the game. 2. Select the Hunter hero. 3. Switch to Hero camera. | A flame effect around the Hunter. | No flame effect.
4 | Fixed - Waiting Confirmation | B - Critical | Engineering | Gameplay | Tony Perez | Yaniel Rivera | 2016-05-18 | First | Game is winnable by going straight to the portal | 1. Start new game 2. Switch to Hero Mode 3. Sprint to the enemy base and get behind it 4. Let the hero auto attack the portal until it is destroyed | Winning the game with little to no effort | A game that requires the player to destroy several towers before winning the game | Towers give the portal extra damage mitigation (up to 100% if all towers are present), and also power the Portals psedo-lazer. Lazer only targets the hero Forcing him to kill the other towers for safety.
5 | Fixed - Waiting Confirmation | C - Minor | Engineering | Character | Young Kim | Young Kim | 2016-05-18 | First | Some particle effects follows the hero when they use their abilities | 1. Start the game 2. Select Tank hero 3. Switch to Hero mode 4. Use any w, e skill and move | Skill particle effects follows the hero when uses the skills and move | Particle effect to stay rather than follow hero
6 | Fixed - Waiting Confirmation | C - Minor | Engineering | Gameplay | Yaniel Rivera | Yaniel Rivera | 2016-05-18 | First | Caster 'Q' and 'E' use aren't intuitive. User needs to hold the space bar to use skills | 1. Start the game 2. Select Caster hero 3. Attempt to use skills | Pressing skills won't activate them nor give any feedback | pressing skills would bring the player to an aiming state where pressing the skill again will activate it where aiming
7 | Fixed - Waiting Confirmation | D - Suggestion | Engineering | Character | Young Kim | Young Kim | 2016-05-18 | First | The mana for some heroes never run out | 1. Start the game 2. Use any skills for the heroes | Mana never ran out even if I spam abilities | Mana to run out and to be forced to choose wisely when to use them
8 | Fixed - Waiting Confirmation | C - Minor | Design | UI | Tony Perez | Young Kim | 2016-05-18 | First | Instruction scene before the game starts shows outdated controls and mechanics | 1. Start a game 2. Before it starts 3. There it is | Old instructions with text that says "to be replaced" | Instructions scene showing the correct controls
9 | Fixed - Waiting Confirmation | D - Suggestion | Design | UI | Tony Perez | Tony Perez | 2016-05-18 | First | No Japanese translation for tutorial instructions | 1. Set Language to Japanese in Options 2. Start Tutorial Level 3. Go through the instructions | English instructions on Japanese setting | Japanese translations for tutorial instructions | (warning: all tutorial translations were done through google translate without being checked)
10 | Fixed - Waiting Confirmation | C - Minor | Engineering | Environment | Tarrent Adams | Tarrent Adams | 2016-05-18 | First | In the tutorial level, the character can walk through part of the portal model, you are able to cross in and out of the small extrusions on the corners | 1. Turn around 2. Walk through the model | The character passed through the model. | The character should colide with the model. | Although this was a duplicate on the test teams side, and was fixed I am marking it as a duplicate here.
11 | Known Shippable - Waiting Confirmation | D - Suggestion | Art | Textures | Tarrent Adams | Tarrent Adams | 2016-05-18 | First | In the tutorial level, the textures on the walls seem to cross one another, causing flickering in the render. | 1. Look at any wall in the tutorial level | The textures flicker | The textures should bee smooth, or look complete
12 | Known Shippable - Waiting Confirmation | B - Critical | Design | UI | Tarrent Adams |  | 2016-05-18 | First | In the tutorial level, the HUD does not scale with the resolution, if you move the resolution of the game after it has started, the HUD tries to remain stationary which causes weird placements. | 1. Start the game 2. move or change the resolution settings | The HUD remained in same location, or attempted to, which caused scaling issues, and starnge placement specualy in the Hero information | The HUD should scale with the resolution, and look uniform.
13 | Fixed - Waiting Confirmation | B - Critical | Design | Gameplay | Tarrent Adams | Tarrent Adams | 2016-05-18 | First | In the tutorial level, The character can skip the entire tutorial, by ignoring the tooltips, and killing the minions he finds on the way, causing them to destroy the tower, and complete the tutorial without ever fighting the large spawn of minions | 1. Start the game 2. Move through the tutorial, ignoring the tooltips 3. Kill the first set of three minions, then go through the door 4. As long as you dont click continue on the tooltips, the next set of minions do not spawn 5. Destroy the tower | Early finish of the tutorial | The tutorial to require you to complete each step in order. | This was fixed both with scale, and coding. It is not almsot impossible to kill all minions and tutorials alone. You also can not spik groups any more.
14 | Open | C - Minor | Engineering | Character | Yaniel Rivera |  | 2016-05-18 | First | Skill particles for 'Q' , 'E' and Aiming show when Hero spawn | 1. Start the game 2. Select caster 3. quickly press 'C' to enter third person 4. Notice skill particles. | Particles are shown | There shouldn't be any particles shown.
15 | Fixed - Waiting Confirmation | D - Suggestion | Design | UI | Tarrent Adams | Tarrent Adams | 2016-05-18 | First | In the tutorial, there is text telling you to press enter to skip the introduction, but it is so hard to read it is almost invisible | 1. Start the tutorial | The text is super hard to see. It is almost invisible | Text should be clear. | Scale and coloration fix
16 | Fixed - Waiting Confirmation | B - Critical | Engineering | UI | Tony Perez | Tony Perez | 2016-05-18 | First | Camera moves around when it shouldn't in tutorial | 1. Start the tutorial 2. Read instructions 3. Move mouse cursor towards continue button | Camera moving around when trying to reach continue button on ui | Camera staying still while instructions are on screen
17 | Fixed - Waiting Confirmation | D - Suggestion | Design | UI | Young Kim | Young Kim | 2016-05-18 | First | There are no numeric values to be seen on the hero's info in game | 1. Start the game | There are no numeric values for the hp or the mana | To have better understanding of the current status of my controlling hero by detailed information in game
18 | Not A Bug - Waiting Confirmation | C - Minor | Design | UI | Yaniel Rivera | Tarrent Adams | 2016-05-18 | First | Big red Arrows are visible in each lane. | 1. Start the game 2. Select character 3. Enter game | Red arrows appear on lanes at all times | Arrows only show when comanding minion to move into a lane
19 | Fixed - Waiting Confirmation | B - Critical | Engineering | Stats | Tony Perez | Tony Perez | 2016-05-18 | First | Mana should be zeroed out on death and fully restored on respawn | 1. Start a game 2. Use some abilities 3. Die | Mana value is maintained and doesn't change | Mana should be full when the hero respawns
20 | Fixed - Waiting Confirmation | D - Suggestion | Design | UI | Tony Perez | Tony Perez | 2016-05-18 | First | Misspelled name in credits | 1. Credits | Cabtrell | Cantrell
21 | Fixed - Waiting Confirmation | C - Minor | Engineering | Combat | Tony Perez | Tony Perez | 2016-05-18 | First | Projectiles follow player around map making them impossible to dodge | 1. Start Game 2. Run to tower 3. Let projectiles chase you around the map | Projectiles chasing after me | Projectiles despawning after short time period
22 | Fixed - Waiting Confirmation | B - Critical | Engineering | Character | Tony Perez | Tony Perez | 2016-05-18 | First | Disable activations of inactive abilities in tutorial | 1. Start Tutorial 2. Press 2, 3, or 4 | Activated abilities | Nothing
23 | Fixed - Waiting Confirmation | C - Minor | Engineering | Sounds | Tony Perez | Tony Perez | 2016-05-22 | First | Siege Minion sound effects aren't using the Audio Manager and are therefore ignoring audio volume settings | 1. Set all volume controls in options to zero volume 2. Play game and get siege minion to spawn | Siege minion making sounds | Siege minion not making sounds
24 | Fixed - Waiting Confirmation | B - Critical | Engineering | Character | Nathan Ralph | Nathan Ralph | 2016-05-22 | First | Hunter W ability doesn't work. | 1. Play as Hunter 2. Use the W ability | W ability not working. | W ability to do something
25 | Fixed - Waiting Confirmation | B - Critical | Engineering | Character | Nathan Ralph | Nathan Ralph | 2016-05-22 | First | Hunter E ability doesn't work. | 1. Play as Hunter 2. Use the E ability | E ability not working. | E ability to do something
26 | Fixed - Waiting Confirmation | B - Critical | Engineering | Stats | Nathan Ralph | Nathan Ralph | 2016-05-22 | First | Minion upgrades persist between games. | 1. Start the game. 2. Purchase upgrades. 3. Close and reopen the game. 4. View clone stats. | Upgrades persisting. | Upgrades resetting. | Created ResetUpgraes() which returns stats to original values at the beginning of each game.
27 | Fixed - Waiting Confirmation | C - Minor | Engineering | Fonts | Tony Perez | Tony Perez | 2016-05-23 | Second | Japanese text in instruction screen was disabled because it was causing crashes on runtime | 1. Set language to Japanese 2. Get to instructions screen | English Instructions | Japanese instructions without crashes
28 | Fixed - Waiting Confirmation | C - Minor | Engineering | Combat | Nathan Ralph |  | 2016-05-23 | Second | Explosive Shot destroys before finishing its animation. | 1. Purchase the explosive shot. 2. Let it fire on an enemy. | The shot effect ends abruptly. | The animation to finish.
29 | Fixed - Waiting Confirmation | B - Critical | Engineering | Input | Tony Perez | Tony Perez | 2016-05-23 | Second | Pressing enter on tutorial button in main menu starts tutorial with Hunter hero | 1. From the main menu, go to the tutorial using the keyboard | Hunter hero | Assassin hero
30 | Known Shippable - Waiting Confirmation | C - Minor | Engineering | Input | Tony Perez | Tony Perez | 2016-05-23 | Second | Rotation in the character selection screen would occasionally make an unnecessary full rotation Kappa | 1. Go to Character Selection 2. Press left,left,right or right,right,left really fast on the keyboard | Rotator turning away from the selected hero and coming back around | Rotator rotating towards selected hero
31 | Fixed - Waiting Confirmation | C - Minor | Engineering | Input | Nathan Ralph |  | 2016-05-23 | Second | Pressing 'C' while in the shop causes the minion lane selection to open and the camera to switch. | 1. Open the Shop. 2. Press C. | The camera switches, the Shop buggs out. | The camera switches and the shop doesn't bug out.
32 | Fixed - Waiting Confirmation | C - Minor | Engineering | Character | Nathan Ralph |  | 2016-05-23 | Second | Hunter E ability projectile sometimes dies before reaching target. | 1. Play as Hunter. 2. Get at max range of a target. 3. Shoot. | The projectile is destroyed before reaching destination. | The projectile hits the target.
33 | Duplicate - Waiting Confirmation | D - Suggestion | Design | Gameplay | Young Kim | Tony Perez | 2016-05-23 | Second | There is no timer for hero respawn | 1. Pick hero and die | No timer to indicate when the hero will respawn | Some form of indication how long my hero respawn would take | Test Team: Issue #41: "...a notification lets you know that you will respawn but there is no timer to let you know how long that will be"
34 | Known Shippable - Waiting Confirmation | A - Crash/Showstoper | Engineering | Gameplay | Yaniel Rivera |  |  |  | Cannot Play LoW on Yaniel's Computer, game crashes | On Yaniel's Laptop: 1. Start game 2. Select any hero 3. just wait 3.1 Or attempt to play | Game rendering is messed up,things disappears, controls are laggy, and... Boom Black screen -> white screen -> game crashed. Message saying "Your windows 8 graphics driver has stopped working and recovered". | To run as it would on all other computer's. | While this is true, there really isn't a way around it and only affects gameplay on that computer. (Why is a windows 7 computer running with a windows 8 graphics driver? who knows)
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100